## Sheet1
User story | Estimate | Priority
As an employee, I want to select items for purchase. | 5 | 1
As an employee, I want to inquire a quote for my items. | 5 | 1
As a a user, I want the program to start with an interactive menu. | 2 | 3
As a user, I want to access the order history. | 3 | 3
As a supervisor, I want ot be able to add or delete items. | 8 | 3
As a user, I should be able to login. | 13 | 2
As a supervisor, I want to be able to add a new user. | 8 | 2 | Product Backlog
As a supervisor, I want to be able to approve or deny an employee request. | 34 | 2
As a user, I want to confirm my order. | 2 | 3
As a developer, I want to see the logic of the code. | 3 | 1
As a developer, I want to see the user's possible interactions with the system. | 13 | 1
As a developer, I want to see how the code is connected. | 2 | 1
As a developer, I want to see the process interactions arranged in time sequence. | 21 | 1
As a user, I want to be able to cancel a pending order. | 34 | 4
As a user, I want an aesthetic user interface. | 55 | 4
User story | Estimate | Priority
As an employee, I want to select items for purchase. | 5 | 1
As an employee, I want to inquire a quote for my items. | 5 | 1
As a supervisor, I want to be able to add or delete items. | 8 | 3 | Sprint 1 Backlog
As a supervisor, I want to be able to add a new user. | 8 | 2
As a developer, I want to see the logic of the code. | 3 | 1
As a developer, I want to see the user's possible interactions with the system. | 13 | 1
As a developer, I want to see how the code is connected. | 2 | 1
As a developer, I want to see the process interactions arranged in time sequence. | 21 | 1
User story | Estimate | Priority
As an employee, I want to select items for purchase. | 5 | 1
As a a user, I want the program to start with an interactive menu. | 2 | 3
As a user, I want to access the order history. | 3 | 3
As a user, I should be able to login. | 13 | 2
As a supervisor, I want to be able to add a new user. | 8 | 2 | Sprint 2 Backlog
As a supervisor, I want to be able to approve or deny an employee request. | 34 | 2
As a user, I want to confirm my order. | 2 | 3
As a developer, I want to see the logic of the code. | 3 | 1
As a developer, I want to see the user's possible interactions with the system. | 13 | 1
As a developer, I want to see how the code is connected. | 2 | 1
As a developer, I want to see the process interactions arranged in time sequence. | 21 | 1
As a user, I want to be able to cancel a pending order. | 34 | 4
As a user, I want an aesthetic user interface. | 55 | 4